## Sheet1
Project | TQ Number | Date Submitted | Question | Submitted by | Submitted To | Answer | Answered by | Answered Date | Resolved
MEMS Power Supply | 1 | 2023-07-27 | What is the clients preferred frequency step change for the carrier signal (50kHz-300kHz)? | Nic | Client | ~10 kHz step is sufficient | Michal | 2023-07-31 | Yes
MEMS Power Supply | 2 | 2023-07-27 | Can the client confirm the modulation index will be fixed at 1 (i.e., 100%)? | Nic | Client | Yes - two states: no modulation or 100% modulation with modulation frequency step ~10 Hz | Michal | 2023-07-31 | Yes
MEMS Power Supply | 3 | 2023-07-27 | What is a reasonable time for the 'fast' over-current protection to kick in? | Nic | Client | Response time in a range of single miliseconds up to tens of miliseconds to prevent device damage. If it can be faster, it would be even better. | Michal | 2023-07-31 | Yes
MEMS Power Supply | 4 | 2023-07-27 | Which controls would you like to control with a digital input? | Nic | Client | Output type (DC/AC), voltage, modulation (ON/OFF), output enable. Optionally: current limit. The digital control can be implemented as physical switches + display/LEDs or serial (USB) communication | Michal | 2023-07-31 | Yes
MEMS Power Supply | 5 | 2023-07-27 | Can we use any microcontroller? or does the client have a preferred microcontroller. | Nic | Client | There is no preference here. | Michal | 2023-07-31 | Yes
MEMS Power Supply | 6 | 2023-07-27 | How distorted can the sine wave be? | Nic | Client | As low as possible (within budget). The group should define what are limitations of particular design. | Michal | 2023-07-31 | Yes
MEMS Power Supply | 7 | 2023-07-27 | For the hardware interlock system, what is the preferred method? | Nic | Client | Key, switch or even exposed jumper should be ok | Michal | 2023-07-31 | Yes
MEMS Power Supply | 8 | 2023-07-27 | Can we provide buttons on the panel instead of a keyboard? | Nic | Client | Yes | Michal | 2023-07-31 | Yes
MEMS Power Supply | 9 | 2023-07-27 | Does the project have to be controlled by a computer? (aka. being plugged into a computer and it controlling the power outputs?) | Nic | Client | No, can be controlled by the buttons and state displayed using LEDs and/or display | Michal | 2023-07-31 | Yes
MEMS Power Supply | 10 | 13/08/2023 Submitted Late | For the testing above 30V needing to be superized by a supervisor is this an AC limit or a peak limit? | Nic | Client | AC Rms | Michal | 2023-08-14 | Yes
MEMS Power Supply | 11 | 13/08/2023 Submitted Late | How would one represent an expected 10 year life cycle without destructive testing? Can we use expected lifetimes, or do we need to perform accelerated testing. | Nic | Client | Use of expected lifetimes should be ok. However, if you determine that it is not enough, please proceed with accelerated testing. | Michal | 2023-08-14 | Yes